Scheme of a ground area receipt by the winner of the auction for the lease right or private property right

- Approval of the report about the auction results

Decision making on a ground area allotment (10 working days)

- Fee payment for the lease contract conclusion right or for the private property right (10 working days)

- Lease contract conclusion between executive committee and the auction winner

- (2 working days)

- Registration of the lease right (private property) by the auction winner in the state registration and land cadastre organization

Scheme of a ground area receipt without the auction

(also for the investment contract realization)

Presentation of a documents pack to the district city executive committee according to point 14 of the Regulation about seizure and allotment of a ground area, approved by the Decree

Consideration of the presented documents in the district city executive committee and preparation of the commission of the land management to prepare land cadastre documentation

(3 working days)

Contractor agreement conclusion between an organization concerned and land management organization

(3 working days)

Carrying out of the design and survey works, agreement and approval of the master plan of the building project

Consideration of the documents at the commission and approval of the act of a ground area choice by the chairman of the local executive committee

(10 working days)

Preparation of the land cadastre documentation for the working of the commission on the ground area location choice

(25 working days from the works payment)

Contractor agreement conclusion with the land management organization for the working out of the ground area siting project

(3 working days)

Working out of the ground area siting project by the organization

(up to 1 month from the works payment day)

Consideration of the siting project, decision making on the ground area allotment to local executive committees

(13 working days)

Fixing of the ground area border – lines on site according to the contractor agreement

(not more than 15 working days)

Scheme of a ground area receipt by the winner of the auction for the right of capital buildings engineering and construction in Brest

Drawing up of the ground area siting project (within 1 month from the presentation of master plan of the building project)

объекта строительства)

Approval of the report about the auction results

Decision making of the city executive committee on the ground area allotment

(10 working days)

Conclusion of the agreement for the realization of the capital buildings engineering and construction, conclusion of the lease contract of a ground area between city executive committee and the auction winner (2 working days)

Fee payment for the conclusion of lease contract of a ground area

(10 working days from the day of the decision making on the ground area allotment)

Registration of the lease right (private property) by the auction winner in the state registration and land cadastre organization